# Example: Risk management

This example is based on the Mentoring Program project used throughout the Project Management website and handbook.

| Risk Description | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Low mentor participation | Medium | High | Expand outreach to faculty, offer recognition incentives |
| Poor mentor-mentee matching | Medium | Medium | Collect preference forms, allow rematching if needed |
| Scheduling conflicts for orientation | High | Medium | Offer multiple session options, record session for flexibility |
| Limited budget for events | Medium | Medium | Seek co-sponsorships, use campus facilities |
| Low mentee engagement after kickoff | Low | High | Regular check-ins, surveys to catch issues early |